## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a User, I want to securely login to access my account. | Must Have | None | Developer | Done
Sprint 1 | Sprint 1 | US-002 | As a Guest, I want to sign up for a new account. | Must Have | None | Developer | Done
Sprint 1 | Sprint 1 | US-003 | As a Staff, I want to add new products to the inventory. | Must Have | US-001 | Developer | Done
Sprint 1 | Sprint 1 | US-004 | As a Staff, I want to view a list of all products. | Must Have | US-003 | Developer | Done
Sprint 2 | Sprint 2 | US-005 | As an Admin, I want to delete obsolete products. | Should Have | US-004 | Developer | Done
Sprint 2 | Sprint 2 | US-006 | As a Staff, I want to search/filter for specific products. | Could Have | US-004 | Developer | Done
Sprint 2 | Sprint 2 | US-007 | As an Admin, I want to see total store value on dashboard. | Should Have | None | Developer | Done
Sprint 2 | Sprint 2 | US-008 | As an Admin, I want to see total staff count on dashboard. | Should Have | US-009 | Developer | Done
Sprint 2 | Sprint 2 | US-009 | As an Admin, I want to view a list of all employees. | Should Have | US-001 | Developer | Done
Sprint 2 | Sprint 2 | US-010 | As an Admin, I want to revoke staff access (delete user). | Should Have | US-009 | Developer | Done
Sprint 3 | Sprint 3 | US-011 | As an Admin, I need email alerts when stock is low (<2). | Must Have | US-003 | Backend Dev | Done
Sprint 3 | Sprint 3 | US-012 | As a Staff, I want to "buy" items to simulate sales. | Should Have | US-004 | Developer | Done
Sprint 3 | Sprint 3 | US-013 | As a Manager, I want to export inventory data to CSV. | Could Have | US-004 | Developer | Done
Sprint 3 | Sprint 3 | US-014 | As a Developer, I want to Dockerize the app for deployment. | Could Have | None | DevOps Eng | Done
Sprint 3 | Sprint 3 | US-016 | As a User, I want a responsive UI for mobile access. | Could Have | None | Frontend Dev | Done
Sprint 3 | Sprint 3 | US-017 | As a Staff, I want toast notifications for success/errors. | Should Have | US-003 | Frontend Dev | Done
Sprint 5 | - | US-018 | As a Staff, I want a Mobile App (Android/iOS) to scan barcodes. | Could Have | US-001 | Mobile Dev | To Do
Sprint 5 | - | US-019 | As a User, I want Social Login (Google/Facebook) for easier access. | Could Have | US-001 | Developer | To Do
Sprint 5 | - | US-020 | As a User, I want to reset my password via Email OTP if I forget it. | Should Have | US-011 | Backend Dev | To Do
Sprint 6 | - | US-021 | As a Manager, I want AI Predictive Analysis to forecast stock demand. | Won't Have | US-013 | Backend Dev | To Do
Sprint 6 | - | US-022 | As an Admin, I want Multi-Warehouse support to track stock across cities. | Won't Have | US-003 | Architect | To Do
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7