## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Dev Team | 2025-11-20 | Startup Failed: Port 8080 already in use by another process. | Sprint 1 | Backend Dev | Environmental | Killed the process using the port and restarted the server. | 2025-11-20 | Closed | Critical blocker for local dev.
2 | QA Team | 2025-11-22 | Login Failed: Old users created before encryption cannot login. | Sprint 2 | Backend Dev | Functional | N/A (Known issue, old users must reset passwords). | - | Closed | Expected behavior after update.
3 | QA Team | 2025-11-23 | API Error: Frontend fails to connect to Backend in Docker. | Sprint 3 | Frontend Dev | Configuration | Updated API Base URL to use service name. | 2025-11-24 | Closed | Critical for Docker deployment.
4 | QA Team | 2025-11-25 | Negative Stock: System allows purchasing more items than available. | Sprint 3 | Backend Dev | Functional | Added validation check in buyProduct method. | 2025-11-26 | Closed | High severity.
5 | UX Team | 2025-11-26 | Product Image: Broken image link displays an unsightly placeholder. | Sprint 3 | Frontend Dev | UI/UX | Pending fix to add a reliable fallback image component. | - | Open | Low priority.
6 | QA Team | 2025-11-27 | Alert Failure: Low stock emails are only sent to one person. | Sprint 4 | Backend Dev | Functional | Updated EmailNotifier to fetch all admins dynamically. | 2025-11-28 | Closed | Fixed before production.
7 | UX Team | 2025-11-28 | Mobile View: Dashboard sidebar overlaps main content on phone. | Sprint 3 | Frontend Dev | UI/UX | Pending CSS adjustment for media queries. | - | Open | Affects mobile usability.
8 | QA Team | 2025-11-29 | Signup: Server Error when signing up with an invalid email. | Sprint 2 | Backend Dev | Functional | Added Email validation annotation to data object. | 2025-11-30 | Closed | Prevents bad data.
9 | DevOps | 2025-12-01 | Database: Container is healthy but connection fails initially. | Sprint 3 | DevOps | Infrastructure | Added wait-for-it script to delay startup. | 2025-12-02 | Closed | Docker Compose timing issue.
10 | Security | 2025-12-02 | CORS Error: Frontend blocked when accessing API from new URL. | Sprint 4 | Backend Dev | Security | Configured CorsConfiguration to allow specific origins. | 2025-12-03 | Closed | Critical for deployment.
11 | QA Team | 2025-12-03 | Buy Modal: Total Price field does not update when quantity changes. | Sprint 3 | Frontend Dev | Functional | Added logic to recalculate total on quantity change. | 2025-12-04 | Closed | Minor UI bug.
12 | QA Team | 2025-12-05 | Delete Risk: Admin can accidentally delete their own account. | Sprint 4 | Backend Dev | Functional | Pending check to prevent self-deletion. | - | Open | High risk.
13 | QA Team | 2025-12-06 | Export CSV: The downloaded filename is generic without a date. | Sprint 3 | Frontend Dev | Functional | Pending update to append timestamp to filename. | - | Open | Usability improvement.
14 | Scale Test | 2025-12-07 | Dashboard Performance: Load time is slow with many products. | Sprint 4 | Backend Dev | Performance | Investigating database indexing and pagination. | - | Open | Optimization needed.
15 | Security | 2025-12-08 | Session: Token remains valid for API calls after user logs out. | Sprint 2 | Backend Dev | Security | Investigating server-side token blacklisting. | - | Open | Standard JWT limitation.